## Sheet3
Monthly Progress
Decentralized Capital Budget Programme - 2018 | [22 empty] | Annexure No.1
Physical and Financial Progress of the Month of SEPTHEMBER - 2018
Divisional Secretariate Division (a) |  |  | Name: Galenbindunuwewa
No:………………………………..
SN | Name of MP | Name of Project | G.N.Division (b) |  | Sector | Type of Project (Construction /Goods & Services) | Total Estimate Cost (Rs.) |  | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical progress (c ) | [9 empty] | No of Beneficiaries | Remarks
[12 empty] | A | B |  |  |  | C | D | E | F | G
|  |  | Name | No |  |  | with vat | without vat |  |  |  |  | B1 | B2 | B3 | B4
1 | Hon. Mr.S.M.Chandrasena | Provide Electrical Inslument to Sri Shaylabimbaramaya Galmaduwa | Dutuwewa Peranigama | 166 | SW | G & S | 50000 | 50000 | 50000 | [7 empty] | 1 |  |  |  |  | 1200
2 | Hon. Mr.S.M.Chandrasena | Provide Inslument to Seelawathi Pre School | 21 Janapadaya West | 179 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 150
3 | Hon. Mr.S.M.Chandrasena | Provide Cementh to Sri Alokaweharaya | 21 Janapadaya Este | 180 | SW | G & S | 30000 | 30000 | 30000 |  |  |  | 1 | [8 empty] | 1100
4 | Hon. Mr.S.M.Chandrasena | Rehabilitation road of Aluthwewa to Mewallawa | Wannankulama | 185 | RA | Constrution |  |  | 150000 |  |  | 1 | [9 empty] | 200
5 | Hon.Mr.S.C.MuthuKumarana | Provide Svili Seet to Delenatharu Pre School Building in Sri Alokaweharaya | 21 Janapadaya Este | 180 | SW | G & S | 50000 | 50000 | 50000 |  |  |  | 1 | [8 empty] | 900
6 | Hon.Mr.S.C.MuthuKumarana | Provide Inslument to Sri gangaram siri siduhath daham scool ulpathgama | Ulpathgama | 158 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 350
7 | Hon.Mr.S.C.MuthuKumarana | Rehabilitation of Aloka pre scool to Paranigama | Dutuwewa Peranigama | 166 | SS | Constrution | 27904.45 | 27904.45 | 25000 |  | Unit 01 |  | 1 | [8 empty] | 300
8 | Hon.Mr.S.C.MuthuKumarana | Provide Chair to Asarana Sarana awamangalyadara socity Sunanda Street | Sunandamawatha | 191 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 450
9 | Hon.Mr.S.C.MuthuKumarana | Provide Chair to Janasirigama sri Gnanarathana daham scool | Janasirigama | 174 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 550
10 | Hon.Mr.S.C.MuthuKumarana | Provide Chair to Rathnamali death donation socity Kubukwewa | Kumbukwewa | 175 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 600
11 | Hon.Mr.S.C.MuthuKumarana | Provide Chair to Kudagalenbidunuwewa Sumithuru death donation socity | Kuda Galenbindunuwewa | 161 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 400
12 | Hon.Mr.S.C.MuthuKumarana | Provide Elcsity Suply to Hurulunikawewa women Grama Development socity | Hurulu nikawewa | 176 | RE | Constrution | 38650 | 38650 | 40000 |  | Unit 01 |  | 1 | [8 empty] | 320
13 | Hon.Mr.S.C.MuthuKumarana | Provide Chair to Eksath Samanala Kreeda socity Konwewa | Konwewa | 156 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 75
14 | Hon.Mr.S.C.MuthuKumarana | Provide Cooking Instrument set for Death Donation Socity Kolongadwewa | Thammannagama | 160 | SW | G & S |  |  | 10000 |  |  | 1 | [9 empty] | 600
15 | Hon.Mr.S.C.MuthuKumarana | Provide Cooking Instrument set for Death Donation Socity Aliwanguwa | Upuldeniya | 155 | SW | G & S | 10000 | 10000 | 10000 |  |  | 1 | [9 empty] | 450
16 | Hon.Mr.S.C.MuthuKumarana | Rehabilitation Agri road with Grevel of Mr' Sirinama's house to Kappaty Kumbura in Ashwayabadiwewa | Galenbindunuwewa | 162 | RA | Constrution |  |  | 500000 |  |  | 1 | [9 empty] | 250
17 | Hon.Mr.S.C.MuthuKumarana | Rehabilitation road with Grevel of Kumbukwewa to Rathmalwetiya School | Kumbukwewa | 175 | RA | Constrution | 479818 | 479818 | 500000 |  | 580 Meter |  | 1 | [8 empty] | 1500
18 | Hon.Mr.S.C.MuthuKumarana | Construction the Culvert in Rathmalwatiya Viharasthanaya to Mr. Nihal's House | Kumbukwewa | 175 | RA | Constrution | 201730.32 | 201730.32 | 200000 |  | Unit 01 |  | 1 | [8 empty] | 200
19 | Hon.Mr.S.C.MuthuKumarana | Rehabilitation road with Grevel of susana bumi to, near the temle Illuppukanniya | Yakalla | 186 | RA | Constrution | 479818 | 479818 | 500000 |  | 580 Meter |  | 1 | [8 empty] | 350
20 | Hon.Mr.S.Semasingha | Rehabilitation Ilubbadayagma play Ground Galenbindunuwewa | Ilukbadayagama | 164 | CD | Constrution | 194411.1 | 194411.1 | 200000 |  | Unit 01 |  | 1 | [8 empty] | 120
21 | Hon.Mr.S.Semasingha | Provide Svili Seet to Dimuthu Pre School Building in Galenbindunuwewa, Getalawa | Getalawa | 172 | SW | G & S | 50000 | 50000 | 50000 |  |  |  | 1 | [8 empty] | 180
22 | Hon.Mr.Chandima Gamage | Rehabilitation water supply system to Sri rajagiri Rjamaha viharaya Kannimaduwa | Galenbindunuwewa | 162 | WS | Constrution | 204794.25 | 204794.25 | 200000 |  | Unit 01 |  | 1 | [8 empty] | 1600
23 | Hon. Mrs. Chandrani Bandara | Provide the Rain hut to Siyablawa farmer's socity | Kudagalenbindunuwewa | 161 | SW | G & S | 50000 | 50000 | 50000 |  |  |  | 1 | [8 empty] | 400
24 | Hon. Mr. A.R.Ishaq | Provide the 500 L Water Tank and Rak to Padikaramaduwa Shawasakthigama Shawasakthi Death Donation socity | Kurunegala Kolaniya | 194 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 850
25 | Hon. Mr. A.R.Ishaq | Provide Chair to sucharithodaya anyonydara socity 19 kanuwa, Gomarayankalla | Ilukbadayagama | 164 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 400
26 | Hon. Mr. A.R.Ishaq | Provide Chair for Getalawa Aluthdiulwewa Vishaka Woman Socity | Getalawa | 172 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 150
27 | Hon. Mr. A.R.Ishaq | Provide Chair to Samagi awamangalyadara socity Matale Kotasa | Karuwalagaswewa | 173 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 350
28 | Hon. Mr. A.R.Ishaq | Provide cubord for Hurulunikawewa, Nithulgollawa Sumudu Woman Socity | Janasirigama | 174 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 75
29 | Hon. Mr. A.R.Ishaq | Provide speakers set for Ekamuthu Kreeda Socity Galenbindunuwewa, Ilikwewa | Allawewa | 178 | SW | G & S | 30000 | 30000 | 30000 |  |  |  | 1 | [8 empty] | 90
30 | Hon. Mr. A.R.Ishaq | Complete Other work and Roof of pathima pre scool in Upuldeniya | Upuldeniya | 155 | SS | Constrution | 54582 | 54582 | 50000 |  | Unit 01 |  | 1 | [8 empty] | 150
31 | Hon.Mr.WeeraKumara Disanayaka | Rehabilitation Pohora Gabadawa in Gatalawa, Karuwalagaswewa of Udara Govi Sanvidanaya | Karuwalagaswewa | 173 | CD | Constrution | 48691.8 | 48691.8 | 50000 |  | Unit 01 |  | 1 | [8 empty] | 300
32 | Hon.Mr.WeeraKumara Disanayaka | Construct getalawa Sri shailatharama viharaya in Gatalawa | Getalawa | 172 | CD | Constrution | 49562.5 | 49562.5 | 50000 |  | Unit 01 |  | 1 | [8 empty] | 675
33 | Hon.Mr.WeeraKumara Disanayaka | Provide Chair for Siwalakulama Seewali death donation Socity | Siwalakulama | 182 | SW | G & S | 15000 | 15000 | 15000 |  |  |  | 1 | [8 empty] | 350
34 | Hon.Mr.WeeraKumara Disanayaka | Rehabilitation the Ground of Yakalla, Iluppukanniya Deewara Gammanaya | Yakalla | 186 | CD | Constrution | 50190.18 | 50190.18 | 50000 |  | Unit 01 |  | 1 | [8 empty] | 120
35 | Hon.Mr.WeeraKumara Disanayaka | Provide Bafel set for Maithri death donation Socity Galwaduwagama | Galwaduwagama | 183 | SW | G & S | 25000 | 25000 | 25000 |  |  |  | 1 | [8 empty] | 325
36 | Hon.Mr.WeeraKumara Disanayaka | Provide sport wear set for sport team in Thodamaduwa vidyalaya | Galwaduwagama | 183 | SW | G & S | 30000 | 30000 | 30000 |  |  |  | 1 | [8 empty] | 200
37 | Hon.Mr.WeeraKumara Disanayaka | Completethe Balance work of Side Wall in Kannimaduwa Viharasthanaya | Galenbindunuwewa | 162 | CD | Constrution |  |  | 50000 |  |  | 1 | [9 empty] | 1600
38 | Hon.Mr.WeeraKumara Disanayaka | Rehabilitation agri road infront of muriyakadawal tank | Muriyakadawala | 181 | RA | Constrution | 197708 | 197708 | 200000 |  |  |  | 1 | [8 empty] | 270
39 | Hon.Mr.WeeraKumara Disanayaka | Complete Other work of Building in Kurunegala Janapadaya Sri Jayawardhanaramaya | Kurunegala Kolaniya | 194 | CD | Constrution |  |  | 50000 |  |  | 1 | [9 empty] | 600
40 | Hon.Mr.WeeraKumara Disanayaka | Provide saspan set to Sngamiththa socity Ellumgasyaya | Dutuwewa Peranigama | 166 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 200
41 | Hon.Mr.WeeraKumara Disanayaka | Provide Inslument to Nuwaragam Janapadaya Padikaramaduwa Ekamuthu death donation socity | Nuwaragam Janapadaya | 195 | SW | G & S | 20000 | 20000 | 20000 |  |  |  | 1 | [8 empty] | 320
42 | Hon.Mr.WeeraKumara Disanayaka | Rehabilitation Agri road with Grevel of Mr' Kiribanda's Mawatha in Muriyakadawala | Muriyakadawala | 181 | RA | Constrution | 192075.63 | 192075.63 | 200000 |  | 315 Meter |  | 1 | [8 empty] | 100
43 | Hon.Mr.WeeraKumara Disanayaka | Construct Mailgaswewa ,Usgollawa bodirukkarama viharasthana toilet complex | Mailagaswewa | 159 | CD | Constrution |  |  | 200000 |  |  | 1 | [9 empty] | 600
44 | Hon.Mr.WeeraKumara Disanayaka | Provide Cementh to Dilenatharu pre scool building in 21 janapadaya este | 21 Janapadaya Este | 180 | SW | G & S | 50000 | 50000 | 50000 |  |  |  | 1 | [8 empty] | 150
45 | Hon.Mr.WeeraKumara Disanayaka | Complete Other work of Building in Galawaduwagama susana bumi | Galwaduwagama | 183 | SS | Constrution | 199166.12 | 199166.12 | 200000 |  | Unit 01 |  | 1 | [8 empty] | 600
46 | Hon.Mr.WeeraKumara Disanayaka | Rehabilitation of Sri jayawardhanarama viharasthana buildin to Kurunagala Janapadaya | Kurunegala Kolaniya | 194 | CD | Constrution | 194350 | 194350 | 200000 |  | Unit 01 |  | 1 | [8 empty] | 900
TOTAL | [6 empty] | 3253452.35 | 3253452.35 | 4265000 | [12 empty] | 21620
[10 empty] | Constrution | 20
[10 empty] | G & S | 26
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos
(c ) - Instructions to fill the Physical Progress
| Description for rating |  |  | Rates |  | Percentage Ranges
| Estimate is being / to be prepared and initial works started |  |  | A |  | (0 - 5)%
| Constructions : Estimates prepared and approved, Bid documents prepared, Quatations called, Tender awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared |  |  | B |  | (6 - 25)%
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  | C |  | (26 - 40)%
| Constructions : 60% Completed Other : Received goods / instruments as per the order |  |  | D |  | (41 - 60)%
| Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  | E |  | (61 - 80)%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  | F |  | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  | G |  | 100%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  | F |  | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  | G |  | 100%
E For Constructions Projects 51% - 75% completed
For Other Projects: Received goods /instruments as per the order
F - For Constructions 76% - 99% completed
For Other Projects: Completed lists of goods and beneficiaries
G For Constructions Projects 100% completed
For Other Projects: Issued goods and instruments to identified institutions / CBOs