## Sheet1
Monthly Progress
SUKITHA PURAWARA Small Town Development Programme - 2018 | [21 empty] | Annexure No.2
Physical and Financial Progress of the Month of SPETEMBER 2018
Divisional Secretariate Division (a) |  | Name: Galenbindunuwewa
No:………………………………..
SN | Name of Project | G.N.Division (b) |  | Sector | Type of Project (Construction /Goods & Services) | Total Estimate Cost (Rs.) |  | Allocation (Rs.) | Expenditure (Rs.) | Unit of Measure | Physical progress (c ) | [9 empty] | No of Beneficiaries | Remarks
[11 empty] | A | B |  |  |  | C | D | E | F | G
|  | Name | No |  |  | with vat | without vat |  |  |  |  | B1 | B2 | B3 | B4
1 | Construction theRoad with Culvert in welekade junctin to track 05 , Mr. R.M. Rajarathna's House | Gomarankalla | 190 | RA | Construction | 999239.55 | 999239.55 | 999239.55 | 0 | 107 M |  |  |  |  | 1 | [5 empty] | 1500
[15 empty] | 1 | [5 empty] | 1500
(a) - Please see the Annexure No.3 for Divisional Secretariate Divisions Names & Nos
(b) - Please see the Annexure No.4 for Grama Niladhari Divisions Names & Nos
(c ) - Instructions to fill the Physical Progress
| Description for rating |  |  |  | Rates |  | Percentage Ranges
| Estimate is being / to be prepared and initial works started |  |  |  | A |  | (0 - 5)%
| Constructions : Estimates prepared and approved, Bid documents prepared, Quatations called, Tender awarded. (25% completed) Other : Identified Institutions / CBO's to provide Goods/ Instruments Obtain required list of goods, Estimated prepared |  |  |  | B |  | (6 - 25)%
| Constructions : Started construction works , (40% completed) Other : Placed orders for goods / instruments |  |  |  | C |  | (26 - 40)%
| Constructions : 60% Completed Other : Received goods / instruments as per the order |  |  |  | D |  | (41 - 60)%
| Constructions : 80% Completed Other : Received goods / instruments as per the order |  |  |  | E |  | (61 - 80)%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  | F |  | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G |  | 100%
| Constructions : 99% Completed Other : Completed lists of goods and beneficiaries |  |  |  | F |  | (81 - 99)%
| Constructions : 100% Completed Other : Issued goods and instruments to identified institutions/ CBOs |  |  |  | G |  | 100%
E For Constructions Projects 51% - 75% completed
For Other Projects: Received goods /instruments as per the order
F - For Constructions 76% - 99% completed
For Other Projects: Completed lists of goods and beneficiaries
G For Constructions Projects 100% completed
For Other Projects: Issued goods and instruments to identified institutions / CBOs